## Executive Summary
AURA ¦ Connector priorities
Decision view | 30 portfolio connectors plus 6 enterprise day-one journeys; validated 2026-10-05
Enterprise Phase One | Phase One Build Wave: Entra + SuccessFactors; SuccessFactors Time Off + Microsoft Graph calendar; SPL National Address; Qiwa; Muqeem + SuccessFactors match; and GOSI + Mudad. API-backed reads remain gated by entitlement or sandbox access, with guided handoffs used where machine access is not approved.
Parallel foundation | OAuth2/OIDC, mTLS as required, secrets, per-tenant permission model, audit, retries/reconciliation, rate limits, test harness and versioning.
Saudi access track | Start sponsor/eligibility and contract discovery now for Nafath, Qiwa, GOSI, Yaqeen, Muqeem and Etimad product selection. Build only after an approved contract and use case.
Commercial focus | Validate SAP pipeline and actual 35% progress. Narrow the first pack to an agreed PR/PO or invoice/status workflow and a customer sandbox.
Largest evidence gap | The 14 guides are project gateway baselines. Most Saudi endpoint paths, issued credentials and production rights cannot be verified on official public pages.
Key decision | Select first customer/tenant, employee journeys, whether AURA executes transactions or presents governed handoffs, and who owns payment/invoice obligations.
Wave | Meaning | Release condition
1 - Build | Documented interface; strong use case | Customer tenant/API product entitlement and approved scenario
2 - Conditional | Documented interface; narrower or higher effort | Confirmed demand, account and test environment
3 - Demand led | Documented but narrow | Named customer and commercial case
D - Discovery | Exact route, identity or access rights unverified | Provider-approved contract, owner, sandbox and use case
Roadmap assumption | Assessment
S/4HANA first; 35% complete | Commercial priority recognized; progress and pipeline are internal claims to validate.
Saudi open API squad | SPL product exists; Etimad product and ZATCA direct vs intermediary scope need specific onboarding.
6–12 / 4–10 / 3–9+ weeks | Roadmap planning ranges; not independently validated delivery commitments.
Enterprise Phase One
Program | Scope | Control
L1 launch core | 4 journeys | Read or guided handoff
L2 access-enabled | 2 journeys | Enable only after entitlement and sandbox
Shared architecture | Elm, stc and Al Rajhi | Customer stack assumptions remain visible gates
Launch guardrail | No transactional writes | Per-connector depth can increase only after approval

## Enterprise Phase One
Enterprise Phase One
Shared Saudi enterprise journey architecture for Elm, stc and Al Rajhi ¦ L1 launch core + L2 access-enabled
Decision: launch read-only services and official handoffs first. Treat customer identity, licensed modules, provider entitlement and sandbox access as explicit release gates. No transactional writes are included.
L1 ¦ Launch core
| Shared enterprise foundation Microsoft Graph + Entra SAP SuccessFactors Gate: confirm each customer's tenant and test access |  |  | J1 ¦ Read Sign in, profile and job info Graph + SuccessFactors Register #1 and #3 |  | J2 ¦ Read Leave status and 'my day' Time Off + Graph calendar Register #1 and #3
|  |  |  | J3 ¦ Read Address verification SPL National Address Register #5 |  | J4 ¦ Handoff Employment contract / certificate Qiwa official service Register #11
L2 ¦ Access-enabled within Phase One
| Release gate Named customer entitlement Provider specification Sandbox + permitted data Keep official handoff until all gates pass |  |  | J5 ¦ Handoff, then Read Residency / Iqama expiry Muqeem + SuccessFactors match Register #15 and #3 |  | J6 ¦ Handoff, then Read Insurance and wage guidance GOSI + Mudad/bank route Register #14 and #20
| Legend | Read | Handoff | Access gate | Source
| Meaning | Display verified customer data | Open official provider journey | Enable API-backed read only after confirmation | Day-one Journeys
| Guardrail | No transactional writes | Provider remains system of record | Missing evidence stays visible | Register and validation log

## Prioritized Connector Register
Rank | Connector | Category | Wave | Priority Score /100 | Access status | Confidence | Use case | AURA value rationale | Recommended integration / data flow | Interface evidence | Access model | Difficulty | Difficulty drivers | Provider onboarding / commercial | Legal / regulatory | Prerequisites / blockers | Open questions | Value 1–5 | Reach 1–5 | Fit 1–5 | Ease 1–5 | Readiness 1–5 | Access 1–5 | Official evidence URL(s) | Detailed connector document | Launch model | Enterprise value 1–5 | Customer access 1–5 | Launch-critical | Launch depth | Enterprise priority index /100 | Enterprise bucket | Enterprise wave | Launch rationale
1 | Microsoft 365 / Microsoft Graph + Entra | Enterprise | 1 - Build | 100 | Build eligible | High | • Employee sign-in and directory profile • Mail, calendar, Teams and file actions in AURA | Broad daily reach and reusable identity/collaboration layer | • Use Entra OAuth2/OIDC for sign-in and Graph REST for selected actions • Choose delegated or app permissions per workflow • Use supported change notifications where needed | Official Graph APIs documented | • Customer Microsoft tenant and app registration • Application permissions need tenant admin consent | Medium | • Least-privilege scopes vary by action • Tenant governance, throttling and notification lifecycle add work | • Register AURA in the customer tenant • Obtain consent for the selected Graph scopes; commercial terms depend on tenant licensing | Not verified as a generic legal requirement | • Customer tenant/admin sponsor and permission matrix • Agree retention rules and initial mail, calendar or file journeys | Which actions require delegated user context versus app-only? | 5 | 5 | 5 | 5 | 5 | 5 | https://learn.microsoft.com/en-us/graph/auth-v2-service?tabs=http | Open detailed assessment | BYO | 5 | 4 | Yes | Read | 92 | 1 Build now | L1 | Identity layer for every other journey. Assumes customers run Entra (to confirm). Build SSO as generic OIDC/SAML with Entra as first adapter.
2 | SAP SuccessFactors | Enterprise | 1 - Build | 98 | Build eligible | High | • Show employee and organization information • Track leave and HR request status where modules support it | Primary HR source for SAP customers | • Use supported OData entities with OAuth2 API client • Sync only approved HR fields; use delta/event capability if enabled • Map external employee IDs and request outcomes | Official OData API documented | • Customer SuccessFactors test/production tenant • API access and role-based permissions set by customer | Medium | • Sensitive HR data needs narrow field scope • Entity permissions, pagination and tenant-specific schema vary | • Register API client in the customer tenant • Grant OData and role-based permissions for selected entities | Not verified as a generic legal requirement | • Test tenant and HR data owner • Confirm licensed modules, field map and leave actions | Which Employee Central modules and leave transactions are licensed? | 5 | 5 | 5 | 5 | 4 | 5 | https://help.sap.com/docs/successfactors-platform/sap-successfactors-api-reference-guide-odata-v2/list-of-sap-successfactors-api-servers |  | BYO | 5 | 4 | Yes | Read | 92 | 1 Build now | L1 | HR system of record for all three enterprises. Needs a customer test/preview tenant. Source of truth for Qiwa/GOSI/Muqeem matching.
3 | SPL National Address | Saudi | 1 - Build | 97 | Build eligible | Medium | • Validate employee or office national address • Use verified address data for onboarding/service delivery | Saudi-local onboarding quality with broad reach | • Subscribe to the applicable SPL API product • Call approved address verification/retrieval operation • Store or cache results only under product terms | Official National Address API advertised | • Developer/business registration is available • Specific API product and production entitlement need confirmation | Medium | • Address matching and incomplete input need handling • Subscription terms, personal data and test cases add work | • Create SPL developer/business account • Confirm relevant product subscription and production terms | Not verified; confirm data handling with SPL/customer | • Obtain sample requests/responses and credentials • Confirm individual-address use and allowed data retention | Does AURA qualify for individual address lookup and production use? | 5 | 4 | 5 | 5 | 5 | 5 | https://splonline.com.sa/en/national-address-api/ | Open detailed assessment | BYO | 4 | 3 | Yes | Read | 72 | 1 Build now | L1 | Day-one journey 3; no government approval needed beyond customer registering for the SPL key. Confirm quota/price in writing.
4 | Qiwa | Saudi | 1 - Build | 96 | Build eligible | Low | • Show employment-contract or job-change status • Guide employee through selected labor service | Major Saudi employee lifecycle value | • Proposed: use partner/customer route only after API rights are confirmed • Otherwise direct user to the official workflow • Do not assume a public execution API | Official service portal; external API unverified | • Qiwa portal services are documented • External API and AURA access rights remain unverified | High | • Employment data and process rules are sensitive • Provider entitlement is unresolved | • Find employer sponsor and chosen Qiwa service • Seek provider agreement and machine-access terms | Not verified | • Choose exact contract/job-change action • Confirm customer authority and supported interface | Is there a supported external interface for the chosen service? | 5 | 5 | 4 | 5 | 5 | 5 | https://qiwa.sa/en/services |  | BYO | 5 | 2 | Yes | Handoff | 76 | 1 Build now | L1 | Highest Saudi employee value; no public API evidenced. Ship guided handoff now (contract review, certificate); API only if Qiwa/HRSD approves.
5 | Muqeem | Saudi | 1 - Build | 95 | Build eligible | Low | • Track expatriate residency or visa services • Present employee status or official handoff | Relevant to Saudi employer mobility workflows | • Proposed: use customer-authorized Muqeem contract if offered • Otherwise provide governed employee handoff • Do not infer API operations | Service product context; external API unverified | • Commercial customer/provider rights may be required • External AURA API entitlement unverified | High | • Immigration data requires careful authorization • Provider approval and transaction rules are unknown | • Confirm employer subscription and partner eligibility • Obtain provider agreement for selected transaction | Not verified | • Specify residency/visa transaction • Confirm authorized tenant and access contract | Is API access offered to AURA for this transaction? | 4 | 5 | 5 | 5 | 5 | 5 | https://elm.sa/en/our-business/digital-products/Pages/security-products.aspx |  | BYO | 4 | 2 | Yes | Handoff | 64 | 1 Build now | L2 | Professional package advertises API; customer-obtainable but AURA integrator rights and spec unverified. Elm is the Muqeem operator: use as access lever.
6 | GOSI | Saudi | 1 - Build | 94 | Build eligible | Low | • Show social-insurance status when authorized • Support employer contribution visibility | Useful for HR verification in Saudi employers | • Proposed: use approved GOSI/customer contract if available • Request technical interface before implementation • Avoid assuming a generic public API | Official e-services; external API unverified | • Official e-services exist • External machine access for AURA is unverified | High | • Government data rights and identity controls are significant • Access route and test data are unresolved | • Obtain employer authority and service scope • Confirm provider-approved route and sandbox | Not verified | • Name data owner and permitted purpose • Secure gateway sponsor, contract and test environment | Can employer obtain sanctioned machine access? | 5 | 3 | 5 | 5 | 5 | 5 | https://www.gosi.gov.sa/GOSIOnline/Services&locale=en_US |  | BYO | 4 | 2 | Yes | Handoff | 64 | 1 Build now | L2 | S2S exists for large companies (Elm/stc/Al Rajhi qualify). Start with read/reconciliation vs SuccessFactors; no writes.
7 | Mudad | Saudi | 1 - Build | 93 | Build eligible | Low | • Show payroll/WPS process status if authorized • Assist employees with salary-related requests | Valuable to HR/payroll customers but narrow employee-facing flow | • Proposed: integrate through customer-approved payroll route • Use governed handoff if external API is unavailable • Do not infer Mudad endpoints | Official platform; external API unverified | • Official platform exists • AURA external API and provider approval unverified | High | • Payroll information is sensitive • Service entitlement and permitted visibility are unclear | • Obtain employer account and payroll owner • Confirm provider contract and machine-access terms | Not verified | • Define employee view versus employer execution • Verify approved data scope and customer sponsor | Is machine interface available and what records may AURA receive? | 4 | 5 | 5 | 5 | 4 | 5 | https://mudad.com.sa/landing-page/what-we-offer |  | BYO | 4 | 2 | Yes | Handoff | 64 | 1 Build now | L2 | Wage-issue journey is high value. Al Rajhi's bank documents an automated WPS route, so employer-side status may come via the bank, not a Mudad API.
8 | SAP S/4HANA | Enterprise | 1 - Build | 84 | Build eligible | Medium | • Create or track procurement requests and orders • Show invoice status, supplier data and selected approvals | Live pipeline and core execution system; roadmap states first enterprise release | • Start with selected OData APIs in the customer S/4 tenant • Use tenant communication and authorized business roles • Map request IDs and reconcile status by supported API/event | Official OData API documented | • Customer-controlled S/4 environment • Only users or integrations with the required business roles | High | • Edition and release change API behavior • Business-role mapping, testing and reconciliation are substantial | • Provision a customer tenant or sandbox and API roles • Sign off the first procurement/invoice scenarios with the customer | Not verified as a generic legal requirement | • Confirm S/4 edition, tenant and scoped roles • Select the first two workflows; verify roadmap progress and access | Validate claimed 35% progress and customer sandboxes; which PR/PO/status actions are in scope? | 5 | 4 | 5 | 3 | 3 | 4 | https://help.sap.com/docs/SAP_S4HANA_ON-PREMISE/91af7f8d3acd47da90d33aaacfcd0d59/dad2402e2ff543e7971d788bf35b12c1.html | Open detailed assessment | Demand-gated | 3 | 4 | No | - | 68 | Demand-gated | - | ERP for procurement/finance. SuccessFactors does not imply S/4: build only when a customer confirms it.
9 | ServiceNow | Enterprise | 1 - Build | 82 | Build eligible | High | • Submit employee IT incidents or service requests • Display approval and ticket status in AURA | Strong employee service desk execution and ticket transparency | • Use approved Service Catalog/Table REST resources • Authenticate with configured OAuth/API identity and ACLs • Map ticket IDs and update status through events or polling | Official REST Table API documented | • Customer ServiceNow instance • API identity needs table/catalog ACLs | Medium | • Catalog items and fields vary by customer • ACLs and two-way status mapping require testing | • Obtain a nonproduction customer instance • Set API identity/OAuth and catalog permissions | Not verified as a generic legal requirement | • Choose exact catalog items and request owner • Agree approval transitions and status mapping | Which catalog items and approval transitions are allowed? | 4 | 4 | 5 | 4 | 3 | 4 | https://www.servicenow.com/docs/r/zurich/api-reference/rest-apis/c_TableAPI.html |  | Demand-gated | 3 | 4 | No | - | 68 | Demand-gated | - | Strong IT/service-desk fit but unknown whether launch customers run it.
10 | Oracle Fusion ERP / HCM | Enterprise | 2 - Conditional | 72 | Build eligible | High | • Read worker and leave information • Create or track procurement requisitions | Large-enterprise alternative to SAP | • Use selected Fusion HCM/Procurement REST resources • Follow the customer environment’s approved authentication policy • Map request IDs and poll or use approved events for status | Official REST resources documented | • Customer Fusion environment and module access • Roles restrict HCM and procurement resources | High | • Security roles and modules differ by customer • Large payloads and environment access complicate testing | • Obtain customer tenant and required module licenses • Provision REST roles and a test environment | Not verified as a generic legal requirement | • Select one HCM and one ERP workflow • Confirm sandbox, roles, field map and data owner | Which modules and customer security policy are present? | 4 | 4 | 4 | 2 | 3 | 4 | https://docs.oracle.com/en/cloud/saas/human-resources/farws/index.html ¦ https://docs.oracle.com/en/cloud/saas/procurement/26c/fapra/api-purchase-requisitions.html |  | Demand-gated | 1 | 4 | No | - | 44 | Demand-gated | - | Customers run SuccessFactors; not needed for launch.
11 | Dynamics 365 / Dataverse | Enterprise | 2 - Conditional | 70 | Build eligible | High | • Create or view customer/employee service cases • Show case progress in AURA | Reusable Microsoft ecosystem extension | • Use Dataverse Web API with Entra OAuth • Choose app user or delegated access and table security roles • Use configured change tracking/events for updates | Official Web API documented | • Customer Dataverse environment • Licensed app/tables and security roles control access | Medium | • Custom tables and business rules differ by tenant • Application-user roles and governance need review | • Register the app and environment application user • Grant only the required table/security roles | Not verified as a generic legal requirement | • Identify the Dynamics workload and target tables • Obtain customer tenant and test records | Which Dynamics app and tables hold employee requests? | 3 | 3 | 4 | 4 | 3 | 4 | https://learn.microsoft.com/en-us/power-apps/developer/data-platform/webapi/overview |  | Demand-gated | 1 | 4 | No | - | 44 | Demand-gated | - | Not evidenced in launch customers' stack.
12 | PayTabs | Saudi | 2 - Conditional | 63 | Build eligible | High | • Collect a fee for an eligible employee service • Reconcile payment before fulfilling the request | Monetization only where AURA owns a payable journey | • Create hosted payment request server-side and redirect user • Verify callback through server query before marking paid • Reconcile timeout, refund and duplicate states | Official PayTabs integration documentation | • Merchant account and commercial onboarding • Server credentials stay with the merchant backend | Medium | • Payment state and callback validation are sensitive • Refunds, reconciliation and ambiguous outcomes need testing | • Sign merchant agreement and obtain profile/server key • Configure sandbox and approved callback URL | Not verified; payment obligations require specific jurisdictional review | • Name merchant of record and paid service • Assign finance owner and settlement process | Who is merchant of record, and which employee services are paid? | 3 | 3 | 3 | 3 | 3 | 4 | https://docs.paytabs.com/manuals/PT-API-Endpoints/Integration-Types-Manuals/Hosted-Payment-Page/HPP-Landing-Page/ |  | AURA-as-party | 2 | 3 | No | - | 48 | Parked: AURA-as-party | - | Merchant-of-record model undecided; most Hub journeys are free to employees.
13 | IATA | Saudi | 3 - Demand led | 45 | Build eligible | Medium | • Validate a travel agency code during vendor onboarding • Record valid/invalid result and freshness | Useful for a narrow travel partner workflow | • Use licensed CheckACode Web Service under IATA contract • Confirm the attached /checkacode route and headers with vendor • Match response by code and retain freshness metadata | Official commercial CheckACode API product | • Commercial IATA product/subscription • Exact attached gateway credential route is not publicly verified | Medium | • Product entitlement and response freshness need agreement • Attached credential format and batch behavior need testing | • Confirm product eligibility and purchase terms • Obtain licensed API contract and test credentials | Not verified | • Confirm travel-agency validation is needed • Approve budget, contract and permitted code use | Is AURA a licensed subscriber, and is the gateway route IATA direct? | 2 | 1 | 2 | 3 | 3 | 3 | https://www.iata.org/en/services/data/travel-agent/global-data-products/checkacode-webservice/ |  | BYO | 1 | 3 | No | - | 36 | 4 Park | - | Supplier onboarding for travel agencies; Employee Hub fit 29.
14 | Nafath | Saudi | D - Discovery | 68 | Discovery required | Low | • Verify national digital identity for an employee journey • Potentially support trusted sign-in or approval | High potential trust and reach | • Proposed: integrate only through an approved identity flow • Request provider contract before selecting endpoints/auth • Use governed handoff while access is unresolved | Official national SSO service; AURA API contract unverified | • Government-approved relying-party route not established for AURA • No public AURA-ready endpoint confirmed | High | • Identity assurance and security testing are demanding • External eligibility and approval are the main gate | • Identify provider sponsor and relying-party eligibility • Confirm onboarding process and entitlement; terms not verified | Not verified | • Confirm AURA/customer eligibility and use case • Obtain approved test environment and technical contract | Can AURA qualify directly or through a licensed integrator? | 5 | 5 | 5 | 1 | 1 | 1 | https://my.gov.sa/en/services/119727 |  | AURA-as-party | 4 | 1 | No | - | 56 | Parked: AURA-as-party | - | Needs AURA/customer as relying party. Keep corporate SSO as normal login; consider step-up for sensitive HR changes later.
15 | Etimad APIs | Saudi | D - Discovery | 64 | Discovery required | Medium | • Show public-sector procurement information • Track a selected government purchase request | Strategic for Saudi government customers | • Register in Etimad developer portal • Subscribe to the exact approved API product • Implement its published contract after catalog/sandbox review | Official developer portal; exact product not selected | • Portal serves eligible beneficiary groups • Entitlement is specific to each API product | Medium | • Available product may not match AURA’s request • Customer eligibility and production subscription need checking | • Create portal account and select API product • Confirm customer eligibility and subscription approval | Not verified | • Name the procurement workflow and API product • Get sandbox access and production-use terms | Which Etimad APIs support AURA’s exact request and who is eligible? | 4 | 2 | 4 | 3 | 2 | 3 | https://apiportal.etimad.sa/en/get-started |  | BYO | 2 | 3 | No | - | 48 | 4 Park | L3 | Government/semi-government products only; none of the launch customers evidenced as in scope.
16 | Absher | Saudi | D - Discovery | 56 | Discovery required | Low | • Guide employees to a government transaction • Show status only if an authorized route exists | Broad recognition but direct execution rights uncertain | • Prefer official employee handoff now • Proposed direct integration only after sanctioned contract and API spec • Keep transaction ownership with authorized party | Official Absher Business portal; direct API unverified | • Official business portal exists • Direct AURA API access is unverified | High | • Government transaction permissions are uncertain • Identity, authorization and transaction ownership add risk | • Confirm whether approved provider route exists • Use handoff design if no sanctioned integration | Not verified | • Select exact employee transaction • Verify enterprise eligibility and provider owner | Does any direct API exist for AURA’s use case? | 4 | 4 | 4 | 1 | 1 | 1 | https://www.absher.sa/wps/portal/business/Home |  | BYO | 3 | 1 | No | Handoff | 44 | 3 Quick win (handoff) | L2 | No public API; official-channel handoff only. Never collect Absher/Nafath credentials or OTPs.
17 | Yaqeen | Saudi | D - Discovery | 53 | Discovery required | Low | • Verify selected employee/beneficiary identity fields • Improve onboarding data quality | Improves data quality and fraud controls for eligible workflows | • Proposed: use an Elm-approved product/partner route • Obtain exact API contract and purpose limits first • Send only approved verification fields | Elm verification service context; exact API unverified | • Commercial/provider-approved access • AURA’s exact API and permitted purpose are unverified | High | • Identity data is sensitive • Eligibility, allowed fields and credential rules need confirmation | • Discuss agreement and intended purpose with Elm • Request test credentials and commercial terms | Not verified | • Define identity-check decision and legal purpose • Confirm eligible customer and provider entitlement | What fields and verification purpose are permitted? | 4 | 3 | 4 | 1 | 1 | 1 | https://elm.sa/en/our-business/digital-products/Pages/security-products.aspx |  | AURA-as-party | 3 | 2 | No | - | 52 | Parked: AURA-as-party | - | Integrator role must be granted by Elm. Elm is a customer: ask for the integrator pathway.
18 | ZATCA Integration Service | Saudi | D - Discovery | 49 | Discovery required | Medium | • Issue an invoice for a paid employee service • Retrieve invoice status or file for finance | Useful finance workflow only when AURA bills locally | • Attached /billing/v3 is an intermediary contract, not direct ZATCA • Direct Fatoora route needs its own EGS specification/onboarding • Reconcile accepted invoice IDs and unknown outcomes | Official Fatoora program; attached intermediary contract unverified externally | • Direct route requires applicable taxpayer/solution onboarding • Intermediary route requires separate gateway agreement | High | • Tax profile, signing/compliance and reconciliation are complex • Gateway rights and exact route must be separated | • Direct: complete applicable Fatoora EGS onboarding • Intermediary: obtain owner-issued credentials and contract | ZATCA e-invoicing rules only if in-scope taxpayer; applicability to AURA Not verified | • Confirm invoicing entity, VAT applicability and billing owner • Choose direct or intermediary route and test in sandbox | Does AURA issue tax invoices? Who owns intermediary contract and credentials? | 3 | 2 | 3 | 2 | 2 | 2 | https://zatca.gov.sa/en/E-Invoicing/SystemsDevelopers/Pages/default.aspx |  | AURA-as-party | 3 | 2 | No | - | 52 | Parked: AURA-as-party | - | Depends on who the taxable seller is; no clear paid employee journey yet.
19 | NIC | Saudi | D - Discovery | 46 | Discovery required | Low | • Check Hajj person eligibility when authorized • Validate/create/cancel worker permit in relevant program | High for pilgrimage-sector operators; limited general hub reach | • Attached guide proposes three separate gateway hosts • Keep person, visitor quota and worker permit credentials distinct • Confirm official contract before any permit write | NIC institution official; gateway interfaces unverified publicly | • Government-approved integration is required • Attached routes do not prove AURA entitlement | High | • Multiple hosts and authentication schemes • Identity data and permit lifecycle need strict testing | • Secure agency sponsor and gateway entitlements • Obtain approved sandbox and field catalogs | Not verified | • Identify pilgrimage customer and permitted purpose • Verify host owners, credentials and sample outcomes | Who owns each gateway and can AURA act on behalf of employer? | 4 | 2 | 3 | 1 | 1 | 1 | https://sdaia.gov.sa/en/Sectors/Nic/Pages/default.aspx |  | BYO | 1 | 2 | No | - | 28 | 4 Park | - | Hajj-sector specific. Revisit only for a Hajj operator customer.
20 | Ministry of Commerce | Saudi | D - Discovery | 44 | Discovery required | Low | • Verify company commercial registration for agent onboarding • Check owner relationship only if authorized | Relevant to external organization validation | • Project proposes token-protected CR and status gateway routes • Official public CR statistics API is a different product • Obtain owner-approved transactional contract before use | Official CR statistics REST; transactional owner APIs not established | • Transactional gateway entitlement unverified • Public statistics API does not grant personal CR access | High | • Identity-data rights and multiple tokens/hosts • Project and official API products do not match | • Find service/gateway owner and customer purpose • Confirm authorized CR lookup and notification agreement | Not verified | • Define CR validation and owner-check rule • Obtain approved sandbox, contract and status catalog | Is transactional CR lookup available to AURA and via which owner? | 3 | 2 | 3 | 2 | 1 | 1 | https://mc.gov.sa/ar/About/Statistics/Documents/MC%20CR%20restapi.pdf |  | BYO | 2 | 1 | No | - | 32 | 4 Park | - | Business-entity checks; low employee value; transactional access unverified.
21 | SADAD | Saudi | D - Discovery | 44 | Discovery required | Low | • Issue a bill reference for a paid service • Reconcile settlement before completion | Alternative payment rail where a biller relationship exists | • Attached intermediary proposes bill creation only • Contract separate status/notification and settlement flow • Reconcile ambiguous bill or payment outcomes | SADAD bill payment official; intermediary route unverified | • Biller/intermediary relationship needed • Attached route is not a public SADAD API | High | • Biller onboarding and settlement gap • Missing status contract prevents end-to-end payment flow | • Confirm registered biller and intermediary agreement • Obtain credentials plus reconciliation feed | Not verified | • Name merchant/biller owner and paid service • Secure settlement contract and test bill data | Who is registered biller? What is status/settlement API? | 3 | 2 | 3 | 2 | 1 | 1 | https://www.sama.gov.sa/en-US/payment/Pages/SADAD.aspx |  | AURA-as-party | 2 | 1 | No | - | 32 | Parked: AURA-as-party | - | Requires biller/sub-biller status; bill creation is not payment confirmation.
22 | Ajeer | Saudi | D - Discovery | 41 | Discovery required | Low | • Show temporary-worker assignment/permit status • Guide an eligible employer service request | Sector-specific employee services | • Proposed: select Ajeer service and approved customer route first • Use official handoff if API rights unavailable • No public API assumed | Official service portal; external API unverified | • Official service portal exists • Customer/provider machine access is unverified | High | • Services have different eligibility rules • Labor approvals and external access create dependencies | • Confirm employer eligibility and chosen service • Request provider agreement/technical route if offered | Not verified | • Choose exact assignment/permit journey • Verify employer authority and supported interface | Which Ajeer service, and does it offer partner machine access? | 3 | 2 | 3 | 1 | 1 | 1 | https://ajeer.qiwa.sa/landing/services |  | BYO | 2 | 2 | No | - | 40 | 4 Park | - | Seasonal/temporary labor; limited fit for these enterprises.
23 | CRS | Saudi | D - Discovery | 37 | Discovery required | Low | • Search hotel availability for staff travel • Reserve, modify or cancel a selected booking | Potential travel benefits, but provider identity unresolved | • Project gateway lists search/details/reservation/cancel routes • Pause until the CRS operator, auth and rights are identified • Reconcile booking reference before retrying writes | Internal gateway inventory only; no identified official vendor API | • CRS vendor identity unresolved • No verified commercial or API access model | Unknown | • Unknown provider and authentication contract • Price changes and booking liability add complexity | • Identify legal CRS vendor and gateway owner • Confirm booking agreement, rates and credentials | Not verified | • Resolve provider identity and travel owner • Obtain test booking, cancellation and reconciliation rules | Which CRS product/company operates this gateway? | 3 | 2 | 2 | 1 | 1 | 1 | https://www.nusuk.sa/umrah |  | BYO | 1 | 1 | No | - | 20 | 4 Park | - | Supplier unidentified; booking liability unresolved.
24 | SAR through Masar Integration Gateway | Saudi | D - Discovery | 37 | Discovery required | Low | • Search and book rail for staff travel • Pay, inquire or cancel using saved booking ID | Sector-specific travel fulfilment | • Attached Masar intermediary uses Basic auth and party-key • Use /sar/shared routes only under approved gateway contract • Inquire after ambiguous book/pay timeout | SAR service official; Masar contract unverified | • Intermediary/partner agreement required • Official SAR site does not confirm Masar gateway rights | High | • Booking and payment need reconciliation • SAR/Masar commercial rights and test accounts are unresolved | • Identify Masar legal operator and SAR commercial route • Obtain party-key, credentials and test account | Not verified | • Confirm travel-booking owner and approved channel • Get booking/payment/cancel test scenarios | Which Masar legal entity and contract grants AURA booking rights? | 3 | 2 | 2 | 1 | 1 | 1 | https://www.sar.com.sa/ |  | BYO | 1 | 1 | No | - | 20 | 4 Park | - | Intermediary authority unverified.
25 | MOFA | Saudi | D - Discovery | 34 | Discovery required | Low | • Register an approved external agent for visa workflow • Track accepted or rejected registration | Narrow travel/pilgrimage operations | • Project guide proposes TIBCO-mediated /sendeadata • Use bearer credential only under owner-approved contract • Reconcile duplicate or timeout before resubmission | Official visa portal; TIBCO route unverified | • Government/partner intermediary approval • Public visa portal does not verify the gateway route | High | • Agent data and duplicate handling require care • Intermediary entitlement and code catalogs are unknown | • Secure agency sponsor and intermediary agreement • Confirm token issuance and permitted agent records | Not verified | • Identify authorized agent and business owner • Obtain current route, codes and sandbox examples | Is TIBCO gateway active and who issues credentials? | 3 | 1 | 2 | 1 | 1 | 1 | https://visa.mofa.gov.sa/ |  | AURA-as-party | 1 | 1 | No | - | 20 | Parked: AURA-as-party | - | Travel-agent registration; indirect employee value.
26 | MOI | Saudi | D - Discovery | 34 | Discovery required | Low | • Create or update an Umrah agent record • Track accepted/rejected agent status | Narrow sector execution use case | • Attached bearer gateway proposes create/update agent calls • Validate provider ownership and status codes first • Reconcile ambiguous create outcomes | Official MOI business service context; exact API unverified | • Government/partner route proposed • Exact MOI gateway entitlement unverified | High | • Agent permission and duplicate writes are sensitive • Gateway ownership and outcome catalog unresolved | • Find agent sponsor and gateway owner • Obtain approved values, token and test contract | Not verified | • Confirm Umrah operator use case • Verify route, entity authority and status catalog | Is this MOI gateway current and available to AURA? | 3 | 1 | 2 | 1 | 1 | 1 | https://www.absher.sa/wps/portal/business/Home |  | BYO | 1 | 1 | No | - | 20 | 4 Park | - | Regulated agent registration; not an employee journey.
27 | Nusuk Imtithal / Sahab | Saudi | D - Discovery | 34 | Discovery required | Low | • Send field-inspection and incident updates • Correlate them to ticket and employee/location | Pilgrimage operations, outside general employee hub | • Project proposes outbound inspection-details POST with client headers • Inbound ticket creation needs a separate contract • Persist acknowledgement and reconcile duplicate updates | Official integration-channel context; exact endpoint unverified | • Government/partner access unverified • Official integration-channel context does not validate this endpoint | High | • Two-direction flow has missing inbound contract • Identity, timestamps and event reconciliation need testing | • Identify program owner and approved use case • Confirm outbound credentials and inbound contract | Not verified | • Obtain inbound event spec and complete outbound URL • Test with approved tickets and UTC timestamp rules | Who owns Sahab endpoint and inbound ticket contract? | 3 | 1 | 2 | 1 | 1 | 1 | https://my.gov.sa/en/services/2832279 |  | AURA-as-party | 1 | 1 | No | - | 20 | Parked: AURA-as-party | - | Hajj inspection workflow; owner and inbound API unverified.
28 | Tasheer Connect | Saudi | D - Discovery | 34 | Discovery required | Low | • Submit a visa/travel service form • Update email, change form or hold request | Travel-specialist request execution | • Project guide proposes /tasheerconnect/1 form routes • Confirm current form/field catalog and bearer contract • Persist request number and accepted state | Official business service context; Connect API unverified | • Partner-only route is proposed • Public Tasheer service page does not verify Connect API | High | • Form catalog and sensitive applicant data vary • Vendor access and change rules need testing | • Confirm Tasheer partnership and service contract • Obtain current catalog, token and sandbox | Not verified | • Name selected form and expected travel volume • Verify field rules and request-state outcomes | Is Connect offered to AURA and under which agreement? | 3 | 1 | 2 | 1 | 1 | 1 | https://vc.tasheer.com/ |  | AURA-as-party | 1 | 1 | No | - | 20 | Parked: AURA-as-party | - | All four routes are writes; visa-form specialist.
29 | Atlas | Saudi | D - Discovery | 29 | Discovery required | Low | • Sync nationality reference data • Sync hotel lookup data for travel workflows | Supporting lookup data for pilgrimage travel, narrow hub relevance | • Project proposes bearer /GetNationalities and /GetHotels routes • Identify Atlas operator before integrating • Page through data and upsert by stable ID | Internal gateway inventory only; identity unresolved | • Atlas operator identity unresolved • No verified data license or API entitlement | Unknown | • Unknown vendor and data provenance • Paging, refresh and entitlement require validation | • Identify legal operator and data license • Confirm gateway contract and service token | Not verified | • Find lookup owner and accepted dataset • Obtain sample pages, IDs and refresh rules | Which Atlas product/company supplies this API? | 2 | 1 | 2 | 1 | 1 | 1 | https://www.nusuk.sa/ |  | BYO | 1 | 1 | No | - | 20 | 4 Park | - | Provider identity unknown; name collides with an unrelated Saudi Atlas.
30 | Kidana | Saudi | D - Discovery | 29 | Discovery required | Low | • Retrieve a Hajj-site handover report file • Deliver it to an authorized employee | Specialized Hajj operations | • Project proposes GET handover file by reportId • Verify endpoint and authorization with Kidana/owner • Validate media type and access before storage | Official organization context; handover API unverified | • Partner/project access unknown • Public Kidana site does not verify file API | High | • File authorization and size/format checks • Program-specific report entitlement is unclear | • Secure Kidana project sponsorship • Confirm report ID scope and authorization contract | Not verified | • Identify Hajj operator and file owner • Confirm permitted storage and test report IDs | Who owns report IDs and may AURA store files? | 2 | 1 | 2 | 1 | 1 | 1 | https://kidana.com.sa/ |  | BYO | 1 | 1 | No | - | 20 | 4 Park | - | Single document-retrieval route; Holy Sites operations only.

## Day-one Journeys
Day-one Journeys
Structured source for the Enterprise Phase One workbook view and website. L2 remains part of Phase One but is access-enabled.
Journey ID | Journey | Connector keys | Connectors | Launch stage | Depth at launch | Depends on | Validation state | Next gate | Primary connector key | Write control | Source note
J1 | Sign in, profile and job info | microsoft-365-graph-entra;sap-successfactors | Microsoft Graph + Entra; SAP SuccessFactors | L1 | Read | Customer Entra app registration; SuccessFactors test tenant | Assumption-gated | Confirm each customer's Entra tenant and provide a SuccessFactors test tenant. | microsoft-365-graph-entra | Read only | Official APIs verified; customer stack remains to be confirmed.
J2 | Leave status and 'my day' | sap-successfactors;microsoft-365-graph-entra | SAP SuccessFactors Time Off; Microsoft Graph calendar | L1 | Read | Time Off module licensed; calendar consent | Licensed-module gate | Confirm Time Off licensing, employee scope and delegated calendar consent. | sap-successfactors | Read only | OData and Graph are documented; tenant modules and consent are customer-specific.
J3 | Address update/verification | spl-national-address | SPL National Address | L1 | Read | Customer SPL registration; quota and price confirmed | Access gate | Register the customer, select the address API product and confirm quota, terms and production use. | spl-national-address | Verify only | Official address APIs and subscription products are published.
J4 | Employment contract / certificate | qiwa | Qiwa | L1 | Handoff | Official deep links; no public API claimed | Handoff only | Confirm official service links and keep employee approval and certification in Qiwa. | qiwa | No writes | Official service journeys are documented; machine access remains unverified.
J5 | Residency / Iqama expiry | muqeem;sap-successfactors | Muqeem; SAP SuccessFactors match | L2 | Handoff, then Read | Elm/customer Professional package; specification and sandbox | Access gate | Confirm customer entitlement, direct-API scope, specification, sandbox and identifier matching. | muqeem | No writes | Public product material indicates an API product; exact AURA rights remain unverified.
J6 | Insurance status and wage-issue guidance | gosi;mudad | GOSI; Mudad or customer bank route | L2 | Handoff, then Read | GOSI S2S eligibility; bank WPS route; sandbox | Access gate | Confirm GOSI S2S eligibility and the customer's bank/Mudad route, permitted status data and test access. | gosi | No writes | GOSI S2S and Al Rajhi automated WPS routes are public; exact customer rights remain gated.

## Scoring & Methodology
Scoring & methodology
Criterion | Weight | Scale (1 → 5) | Evidence and interpretation
AURA use-case value | 25 | 1 marginal; 3 useful; 5 core request execution | Pipeline value considered here; roadmap claim noted where not independently verified
Employee reach | 15 | 1 niche sector; 3 subset; 5 broad daily use | Reach is expected AURA adoption, not provider market share
Strategic fit | 20 | 1 peripheral; 3 adjacent; 5 core hub/enterprise system | Direct relevance to employee hub and reusable architecture
Implementation ease | 15 | 1 very hard/unknown; 3 medium; 5 low effort | Inverse of difficulty; includes testing, operations and data complexity
Dependency readiness | 10 | 1 missing sponsor/spec; 3 potential tenant; 5 ready sandbox | Roadmap planning claim alone does not prove a live sandbox
Access feasibility | 15 | 1 rights unavailable/unverified; 3 enrollment/contract; 5 self-service | Public docs do not imply AURA has production entitlement
Formula / rule | Definition
Priority score | ROUND(weighted sum of the six 1–5 ratings / 5, 0). The six weights sum to 100. This is the only numeric priority score.
Access status | Build eligible when the documented interface/access route, or an approved Phase One guided handoff, can be delivered with customer or provider onboarding; otherwise Discovery required.
Ranking | Build eligible connectors first, ordered by descending Priority Score; then Discovery required connectors ordered by score. Rank is a snapshot; sort again after changing inputs.
Wave 1 | Build eligible with Priority Score ≥80. Customer tenant/product entitlement and scenario sign-off remain release prerequisites.
Wave 2 / 3 | Build eligible with Priority Score 60–79 / <60, respectively.
Discovery gate | Exact provider identity, supported interface or AURA integration rights unverified: D regardless of score. Start access discovery in parallel with build waves.
Evidence rule | Use official pages to confirm provider interface and access; project guides are proposed/owner baselines, not proof of AURA entitlement.
Permissions | Provider onboarding and commercial agreement separated from law. Legal field says Not verified unless an applicable official requirement is established.
Difficulty | Unknown when provider identity/access makes engineering assessment unreliable; otherwise includes integration, testing and operations.
Direct route | Direct is an approach under each provider, never a separate connector row.
Scope | Exactly 24 named Saudi services and 6 enterprise systems. Composite names retained as requested.
Checked | 2026-09-29
Enterprise launch model
Input | Value | Definition
Weight: enterprise value | 60% | Importance to employees of Elm, stc and Al Rajhi under the shared launch model.
Weight: customer-obtainable access | 40% | Likelihood the customer can obtain credentials or a contract in one to two quarters.
Value threshold: high | 4 | Value at or above this level is high.
Value threshold: medium | 3 | Value equal to this level is medium.
Access threshold: ready | 3 | Access at or above this level is realistically customer-obtainable.
No-write launch control | Read or handoff | Contract acceptance, payroll submission, visa and residency actions remain in provider systems.
Check: weights sum | 100% | Must equal 100%.
Enterprise launch rule | Result | Interpretation
Not BYO: AURA must be the approved party | Parked: AURA-as-party | Do not imply customer-obtainable access.
Demand-gated system | Demand-gated | Build only when a named customer confirms the system and journey.
Launch-critical or high value + ready access | 1 Build now | Include in L1 when the journey is read-only or handoff.
High value, access below ready | 2 Negotiate access | Keep in L2 until entitlement and test access are confirmed.
Medium value | 3 Quick win (handoff) | Use an official handoff when it provides employee value.
Below medium value | 4 Park | Do not schedule for Phase One.

## Sources & Discrepancies
Sources & discrepancies
Source ID | Connector / claim | Source type | Official URL / project file | Checked | Supports | Conflict or unresolved point
R0 | Roadmap priority and parallel squads | Project roadmap | AURA_Component_Roadmap_Interactive_v2.html, Enterprise & Saudi Connectors | 2026-09-29 | S/4 priority #1; 35% claim; squads, estimates and dependencies | 35%, pipeline, timeboxes and Saudi quick-win access are internal claims; confirm with owners.
GRAPH | Microsoft 365 / Microsoft Graph + Entra | Official provider | https://learn.microsoft.com/en-us/graph/auth-v2-service?tabs=http | 2026-09-29 | Application permissions and admin consent for Graph | Roadmap says 4–8 weeks; effort depends on exact scopes and tenants.
S4 | SAP S/4HANA | Official provider | https://help.sap.com/docs/SAP_S4HANA_ON-PREMISE/91af7f8d3acd47da90d33aaacfcd0d59/dad2402e2ff543e7971d788bf35b12c1.html | 2026-09-29 | Purchase requisition OData V4; authorized roles required | Roadmap 35% and 8–12 week estimate are internal assertions, not independently verified.
SF | SAP SuccessFactors | Official provider | https://help.sap.com/docs/successfactors-platform/sap-successfactors-api-reference-guide-odata-v2/list-of-sap-successfactors-api-servers | 2026-09-29 | SuccessFactors OData API servers documented | Roadmap 6–10 week estimate not independently validated.
SN | ServiceNow | Official provider | https://www.servicenow.com/docs/r/zurich/api-reference/rest-apis/c_TableAPI.html | 2026-09-29 | ServiceNow Table API documented | Roadmap timing is planning estimate.
SPL | SPL National Address | Official provider | https://splonline.com.sa/en/national-address-api/ | 2026-09-29 | National Address API offered; registration/product access to confirm | Roadmap calls this an open quick win; exact product access and production terms still need confirmation.
ORACLE | Oracle Fusion ERP / HCM | Official provider | https://docs.oracle.com/en/cloud/saas/human-resources/farws/index.html | 2026-09-29 | Fusion HCM REST API documented | Roadmap 8–12 weeks assumes accessible tenant and narrow pack.
ORACLEPR | Oracle Fusion ERP / HCM | Official provider | https://docs.oracle.com/en/cloud/saas/procurement/26c/fapra/api-purchase-requisitions.html | 2026-09-29 | Procurement requisition REST resource | Roadmap 8–12 weeks assumes accessible tenant and narrow pack.
DV | Dynamics 365 / Dataverse | Official provider | https://learn.microsoft.com/en-us/power-apps/developer/data-platform/webapi/overview | 2026-09-29 | Dataverse Web API documented | Roadmap groups this with ServiceNow; use case depends on tenant.
PAY | PayTabs | Official provider | https://docs.paytabs.com/manuals/PT-API-Endpoints/Integration-Types-Manuals/Hosted-Payment-Page/HPP-Landing-Page/ | 2026-09-29 | Hosted payment API integration documentation | Project guide /request and /query align conceptually; exact fields/region endpoints need merchant docs.
P-02 | PayTabs | Project guide | 02-02-paytabs.docx | 2026-09-29 | Gateway route/auth/payload proposal; not proof of production access | Project guide /request and /query align conceptually; exact fields/region endpoints need merchant docs.
NAF | Nafath | Official provider | https://my.gov.sa/en/services/119727 | 2026-09-29 | National single sign-on service; AURA onboarding/API unverified | Roadmap correctly calls this gated; no public implementation contract established.
QIW | Qiwa | Official provider | https://qiwa.sa/en/services | 2026-09-29 | Qiwa services; external API access unverified | Roadmap access track is appropriate; portal service is not evidence of open API.
ETI | Etimad APIs | Official provider | https://apiportal.etimad.sa/en/get-started | 2026-09-29 | Developer portal access steps; exact AURA procurement product to confirm | Roadmap assumes sandbox now/production later; product-specific access remains unverified.
ABS | Absher | Official provider | https://www.absher.sa/wps/portal/business/Home | 2026-09-29 | Absher Business service; direct API unverified | Roadmap says Absher direct on demand; portal does not prove a direct API.
GOS | GOSI | Official provider | https://www.gosi.gov.sa/GOSIOnline/Services&locale=en_US | 2026-09-29 | GOSI electronic services; external API access unverified | Roadmap gated timing reflects provider dependency, not engineering estimate.
MUQ | Muqeem | Official provider | https://elm.sa/en/our-business/digital-products/Pages/security-products.aspx | 2026-09-29 | Elm product context; Muqeem API rights unverified | Roadmap lists gated service; no public API contract verified.
YAQ | Yaqeen | Official provider | https://elm.sa/en/our-business/digital-products/Pages/security-products.aspx | 2026-09-29 | Elm verification product context; exact API rights unverified | Public product context does not validate attached-style generic national API access.
ZAT | ZATCA Integration Service | Official provider | https://zatca.gov.sa/en/E-Invoicing/SystemsDevelopers/Pages/default.aspx | 2026-09-29 | Official e-invoicing developer guidance; intermediary paths not established | Roadmap labels ZATCA sandbox; guide documents non-ZATCA billing gateway routes.
P-01 | ZATCA Integration Service | Project guide | 01-01-zatca.docx | 2026-09-29 | Gateway route/auth/payload proposal; not proof of production access | Roadmap labels ZATCA sandbox; guide documents non-ZATCA billing gateway routes.
NIC | NIC | Official provider | https://sdaia.gov.sa/en/Sectors/Nic/Pages/default.aspx | 2026-09-29 | NIC institutional scope; attached routes not established | Guide endpoints are project-owned contract claims, not public NIC API documentation.
P-04 | NIC | Project guide | 04-04-nic.docx | 2026-09-29 | Gateway route/auth/payload proposal; not proof of production access | Guide endpoints are project-owned contract claims, not public NIC API documentation.
IATA | IATA | Official provider | https://www.iata.org/en/services/data/travel-agent/global-data-products/checkacode-webservice/ | 2026-09-29 | CheckACode commercial web service exists; gateway route differs | Official product exists; attached headers/endpoint not confirmed by public product page.
P-14 | IATA | Project guide | 14-14-iata.docx | 2026-09-29 | Gateway route/auth/payload proposal; not proof of production access | Official product exists; attached headers/endpoint not confirmed by public product page.
MC | Ministry of Commerce | Official provider | https://mc.gov.sa/ar/About/Statistics/Documents/MC%20CR%20restapi.pdf | 2026-09-29 | Official CR statistics REST API; not personal CR or notification gateway | Official CR statistics API is not evidence for personal relationship or /UpdateCRStatus routes.
P-06 | Ministry of Commerce | Project guide | 06-06-ministry-of-commerce.docx | 2026-09-29 | Gateway route/auth/payload proposal; not proof of production access | Official CR statistics API is not evidence for personal relationship or /UpdateCRStatus routes.
MUD | Mudad | Official provider | https://mudad.com.sa/landing-page/what-we-offer | 2026-09-29 | Mudad payroll/wage services; API unverified | Roadmap on-demand stance is consistent with unverified interface.
SAD | SADAD | Official provider | https://www.sama.gov.sa/en-US/payment/Pages/SADAD.aspx | 2026-09-29 | SADAD service existence; not the attached biller gateway contract | Project guide defines bill creation only; official SADAD overview does not validate route or settlement.
P-03 | SADAD | Project guide | 03-03-sadad.docx | 2026-09-29 | Gateway route/auth/payload proposal; not proof of production access | Project guide defines bill creation only; official SADAD overview does not validate route or settlement.
AJE | Ajeer | Official provider | https://ajeer.qiwa.sa/landing/services | 2026-09-29 | Ajeer labor services; API unverified | Roadmap on demand; official site shows services, not external API.
CRS | CRS | Official provider | https://www.nusuk.sa/umrah | 2026-09-29 | Travel ecosystem context only; CRS vendor/rights not identified | CRS is a hotel reservation role, not a uniquely identified provider.
P-10 | CRS | Project guide | 10-10-crs.docx | 2026-09-29 | Gateway route/auth/payload proposal; not proof of production access | CRS is a hotel reservation role, not a uniquely identified provider.
SAR | SAR through Masar Integration Gateway | Official provider | https://www.sar.com.sa/ | 2026-09-29 | SAR rail service; Masar gateway rights/routes not established | Official SAR customer site does not validate Masar routes or party key.
P-11 | SAR through Masar Integration Gateway | Project guide | 11-11-sar-masar-gateway.docx | 2026-09-29 | Gateway route/auth/payload proposal; not proof of production access | Official SAR customer site does not validate Masar routes or party key.
MOFA | MOFA | Official provider | https://visa.mofa.gov.sa/ | 2026-09-29 | Visa service existence; TIBCO registration route not established | Official visa portal does not establish the guide’s intermediary endpoint.
P-07 | MOFA | Project guide | 07-07-mofa.docx | 2026-09-29 | Gateway route/auth/payload proposal; not proof of production access | Official visa portal does not establish the guide’s intermediary endpoint.
MOI | MOI | Official provider | https://www.absher.sa/wps/portal/business/Home | 2026-09-29 | MOI business channel existence; Umrah-agent route not established | Guide uses MOI label but endpoint ownership/directness is unverified.
P-05 | MOI | Project guide | 05-05-moi.docx | 2026-09-29 | Gateway route/auth/payload proposal; not proof of production access | Guide uses MOI label but endpoint ownership/directness is unverified.
NUS | Nusuk Imtithal / Sahab | Official provider | https://my.gov.sa/en/services/2832279 | 2026-09-29 | Nusuk integration channel exists; inspection details contract unverified | Official integration channel does not validate this inspection gateway; guide covers outbound only.
P-09 | Nusuk Imtithal / Sahab | Project guide | 09-09-nusuk-imtithal-sahab.docx | 2026-09-29 | Gateway route/auth/payload proposal; not proof of production access | Official integration channel does not validate this inspection gateway; guide covers outbound only.
TAS | Tasheer Connect | Official provider | https://vc.tasheer.com/ | 2026-09-29 | Tasheer visa-center service; Connect API not publicly verified | Guide contract has no independently verifiable public Tasheer API.
P-08 | Tasheer Connect | Project guide | 08-08-tasheer-connect.docx | 2026-09-29 | Gateway route/auth/payload proposal; not proof of production access | Guide contract has no independently verifiable public Tasheer API.
ATL | Atlas | Official provider | https://www.nusuk.sa/ | 2026-09-29 | Travel ecosystem context only; Atlas operator unverified | Atlas describes data in guide; official operator not identifiable.
P-13 | Atlas | Project guide | 13-13-atlas.docx | 2026-09-29 | Gateway route/auth/payload proposal; not proof of production access | Atlas describes data in guide; official operator not identifiable.
KID | Kidana | Official provider | https://kidana.com.sa/ | 2026-09-29 | Kidana organization; handover API not publicly verified | Public provider page does not verify handover endpoint.
P-12 | Kidana | Project guide | 12-12-kidana.docx | 2026-09-29 | Gateway route/auth/payload proposal; not proof of production access | Public provider page does not verify handover endpoint.
Enterprise launch validation and gates
Type | Item | Status | Evidence / basis | Decision | Next gate | Official URL
Official evidence | Microsoft Graph + Entra | Validated | Official documentation confirms delegated and app-only access with permissions and consent. | Use for identity and selected read journeys. | Confirm each customer's tenant, consent policy and least-privilege scope. | https://learn.microsoft.com/en-us/graph/auth/auth-concepts
Official evidence | SAP SuccessFactors | Validated | Official OData documentation confirms OAuth2 client registration and tenant API access. | Use as the employee and job source of truth. | Confirm test tenant, licensed modules, entities and field permissions. | https://help.sap.com/docs/successfactors-platform/sap-successfactors-api-reference-guide-odata-v2/registering-your-oauth2-client-application
Official evidence | SPL National Address | Validated with access gate | Official portal publishes verification APIs and subscription products. | Include read-only verification in L1. | Confirm customer subscription, quota, pricing, terms and production approval. | https://nationaladdressapis.developer.azure-api.net/apidocumentation
Official evidence | GOSI | Validated with access gate | Official site documents system-to-system integration for large companies. | Keep handoff first; enable read only after entitlement. | Confirm customer eligibility, certificate process, permitted data and sandbox. | https://www.gosi.gov.sa/GOSIOnline/E-Services_Channels?locale=en_US
Official evidence | Mudad / Al Rajhi | Validated customer route | Al Rajhi documents automated WPS upload to Mudad for payroll customers. | Use bank route as a customer-specific option, not a general Mudad API. | Confirm each customer's bank route, status feedback and data rights. | https://www.alrajhibank.com/en/Business/Cash-Management/payroll/WPS
Official workflow | Qiwa | Handoff only | Official services document employment contracts and certificates; public machine access is not established. | Use official deep links and keep approvals in Qiwa. | Obtain written API/partner evidence before any provider-backed read. | https://www.hrsd.gov.sa/id/node/5566195
Public product evidence | Muqeem | Access gate | Public material indicates a Professional/API product context but does not establish AURA entitlement. | Use handoff first; L2 read is conditional. | Confirm customer package, integrator rights, specification, sandbox and pricing. | https://muqeem.sa/
Customer assumption | Enterprise identity and applications | Unconfirmed | SuccessFactors is stated; Entra is believed; stc stack was not evidenced. | Use one shared architecture with per-customer configuration. | Confirm Elm, stc and Al Rajhi identity, HR, payroll and module inventory.
Launch control | Transactional writes | Excluded | Internal launch decision based on legal and operational consequence. | Read-only APIs and official handoffs only. | Increase depth per connector only after customer and provider approval.
Attached model data fixes
Issue | Disposition | Status | Reason
PayTabs and IATA scores were blank in an earlier register | Master retains calculated scores 63 and 45 | Resolved | The existing portfolio formulas already contain the recalculated values.
Rank was not monotonic with score | Keep portfolio rank separate from enterprise launch index | Explained | Access gates and the launch model answer a different decision.
Revised GOSI, Muqeem and Yaqeen scores were not reflected in rank | Do not rewrite historical portfolio rank | Retained | The enterprise model adds a separate priority index and bucket.
Ministry of Commerce and Mudad tied at 44 | Enterprise model prioritizes Mudad for the launch | Resolved for launch | Original portfolio rank remains intact.
MOFA, Nusuk and Atlas ranks were not individually stated | Use master ranks 25, 27 and 29 | Resolved | The master workbook already assigns individual ranks.
Employee Hub score was inconsistent | Use enterprise value plus access | Resolved for launch | The new model defines one decision-specific value axis.
Absher, Nafath, NIC and MOI were confused | Keep separate connector rows and briefings | Resolved | Separate owners, contracts and journeys remain visible.
External gateway owner was assumed | Treat ownership and entitlement as gates | Retained gate | Customer-obtainable access is not inferred from an interface name.